## Onboarding Tracker
Customer ID | Customer / Account | Customer Contact | Start Date | Target Go-Live | Onboarding Stage | Status | Risk Level | Next Action | Next Follow-Up Date | Latest Note | Days to Target
CS-001 | Northstar Learning | Amina Yusuf | 2026-10-12 | 2026-10-13 | Kickoff completed | In progress | Low | Send setup guide | 2026-10-22 | Customer confirmed kickoff; setup guide still needed. | -8
CS-002 | BrightPath Retail | Daniel Reed | 2026-10-14 | 2026-10-15 | Data import | Blocked | High | Resolve CSV formatting issue | 2026-10-21 | Customer reports import errors; support investigation required. | -6
CS-003 | Cedar & Co | Priya Shah | 2026-10-16 | 2026-10-17 | Training | In progress | Medium | Schedule admin training | 2026-10-23 | Training date not yet confirmed. | -4
CS-004 | Summit Works | Leo Martin | 2026-10-17 | 2026-10-18 | First value milestone | Completed | Low | Request onboarding feedback | 2026-10-24 | Customer completed initial workflow and confirmed success. | -3
CS-005 | Harbor Health Demo | Nora Kim | 2026-10-19 | 2026-10-20 | Kickoff | Not started | Medium | Confirm kickoff availability | 2026-10-22 | Waiting for customer to select a kickoff time. | -1

## Summary
Metric | Formula / value
Total accounts | 5
In progress | 2
Blocked | 1
High risk | 1
Completed | 1